## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
e-Commerce website for on line shopping
Group33 |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead | Violet | Avocado | Showily | Red
Project Start Date: | 2021-10-11 |  |  |  |  | October | [20 empty] | November | [27 empty] | December
Scrolling Increment: | 4 | time axis 2021-10-15 to 2021-12-09
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-10-15 to 2021-12-09
Itertion 1
Itertion1 planning and meeting | Goal | Violet | 25% | 2021-10-11 | 1
Complete stakeholder register | High Risk | Avocado | 100% | 2021-10-12 | 5
Design persona | Low Risk | Showily | 50% | 2021-10-17 | 8
Review and test persona | Med Risk | Red | 75% | 2021-10-21 | 4
Complete progess report | On Track | Violet | 100% | 2021-10-25 | 3
Miestones 01 | Milestone | Avocado | 10% | 2021-10-28 | 1 | bar: 2021-10-28
Itertion 2
Itertion2 planning and meeting | Goal | Showily | 55% | 2021-11-01 | 2 | 2021-11-01: 2; 2021-11-02: 2
Preliminary understanding and application Gantt Chart template | High Risk | Red | 90% | 2021-11-02 | 6
Complete a Resource Requirement List for the project | Low Risk | Violet | 70% | 2021-11-05 | 11
Complete files push to Github repository and resolve all issues | On Track | Avocado | 90% | 2021-11-10 | 4
Milestones 02 | Milestone | Showily | 30% | 2021-11-14 | 3 | bar: 2021-11-14 to 2021-11-16
Itertion 3
Itertion3 planning and meeting | Goal | Red | 30% | 2021-11-15 | 4 | 2021-11-15: 2; 2021-11-16: 2; 2021-11-17: 2; 2021-11-18: 2
Complete a Risk Register | High Risk | Violet | 100% | 2021-11-18 | 14
Complete the User Acceptance Test Results template | Med Risk | Avocado | 65% | 2021-11-27 | 6
Push the files to GitHub | On Track | Showily | 100% | 2021-12-02 | 3
Milestones 03 | Milestone | Red | 30% | 2021-12-05 | 19 | bar: 2021-12-05 to 2021-12-09
Formulas:
Violet = IFERROR(IF(MIN(Milestones4352[Start])=0,TODAY()-29,B11(Milestones4352[Start])),TODAY()-29)
Red = [Red, row above]+1

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-11-09 |  |  |  |  | November | [20 empty] | December
Scrolling Increment: | 1 | time axis 2021-11-10 to 2022-01-04
Milestone description | Category | Assigned to | Progress | Start | Days | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
TITLE 1
Task 1 | Goal | Name | 25% | 2021-11-09 | 3 | W: 2; T: 2
Task 2 | Milestone |  |  | 2021-11-14 | 1 | bar: S
Task 3 | Low Risk |  | 50% | 2021-11-06 | 10
Task 4 | Milestone |  |  | 2021-11-29 | 1 | bar: M
Task 5 | Med Risk |  | 10% | 2021-11-15 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-11-15 | 13
Task 2 | On Track |  | 50% | 2021-11-17 | 9
Task 3 | Low Risk |  | 33% | 2021-11-22 | 11
Task 4 | Milestone |  |  | 2021-11-24 | 1 | bar: W
Task 5 |  |  |  | 2021-11-25 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-11-24 | 4
Task 2 | Med Risk |  |  | 2021-11-27 | 14
Task 3 | On Track |  |  | 2021-12-12 | 6
Task 4 | Goal |  |  | 2021-12-16 | 3 | T: 2; F: 2; S: 2
Task 5 | Low Risk |  |  | 2021-11-15 | 19
TITLE 4
Task 1 |  |  |  | 2021-12-19 | 15
Task 2 |  |  |  | 2022-01-02 | 5
Task 3 | Milestone |  |  | 2022-02-13 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-11-09 |  |  |  |  | November | [20 empty] | December | [27 empty] | January
Scrolling Increment: | 5 | time axis 2021-11-14 to 2022-01-08
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-11-14 to 2022-01-08
TITLE 1
Task 1 | Goal | Name | 25% | 2021-11-09 | 3
Task 2 | Milestone |  |  | 2021-11-14 | 1 | bar: 2021-11-14
Task 3 | Low Risk |  | 50% | 2021-11-06 | 10
Task 4 | Milestone |  |  | 2021-11-29 | 1 | bar: 2021-11-29
Task 5 | Med Risk |  | 10% | 2021-11-15 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-11-15 | 13
Task 2 | On Track |  | 50% | 2021-11-17 | 9
Task 3 | Low Risk |  | 33% | 2021-11-22 | 11
Task 4 | Milestone |  |  | 2021-11-24 | 1 | bar: 2021-11-24
Task 5 |  |  |  | 2021-11-25 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-11-24 | 4
Task 2 | Med Risk |  |  | 2021-11-27 | 14
Task 3 | On Track |  |  | 2021-12-12 | 6
Task 4 | Goal |  |  | 2021-12-16 | 3 | 2021-12-16: 2; 2021-12-17: 2; 2021-12-18: 2
Task 5 | Low Risk |  |  | 2021-11-15 | 19
TITLE 4
Task 1 |  |  |  | 2021-12-19 | 15
Task 2 |  |  |  | 2022-01-02 | 5
Task 3 | Milestone |  |  | 2022-02-13 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one